## New location opening timeline
New location opening timeline
120 days out to day 30, for an operator opening their next unit · Free template · Restaurant Codex · restaurantcodex.com
Location
Target open date
Opening lead
Version
Section | Item | Done | Initials | Time
120 to 90 days out | Lease signed, contingencies cleared and the certificate-of-occupancy timeline confirmed with the landlord. | ☐
120 to 90 days out | Building permit and health department plan review filed with the local authority. | ☐
120 to 90 days out | Liquor license application filed, if the unit will serve alcohol. | ☐
120 to 90 days out | General contractor signed; build-out schedule set with a start date and a target completion date. | ☐
120 to 90 days out | Opening budget built: build-out, equipment, initial inventory, pre-opening payroll and a cash reserve for the first 90 days. | ☐
120 to 90 days out | Break-even model built: fixed monthly costs and contribution margin percent calculated, break-even sales set as the target. (Fixed costs / contribution margin %) | ☐
120 to 90 days out | GM named for the new store and start date confirmed. | ☐
120 to 90 days out | Hiring plan drafted: roles, headcount and wage rate by position set for the local market. | ☐
120 to 90 days out | POS vendor contract signed; menu build started in the system. | ☐
120 to 90 days out | Core vendor accounts opened: food distributor, produce, linen, trash and pest control. | ☐
120 to 90 days out | Signage ordered: exterior sign, menu boards, and any permit the sign itself requires. | ☐
120 to 90 days out | Utility accounts opened (power, gas, water, internet) with connection dates confirmed before build-out starts. | ☐
60 days out | Health department inspection date scheduled with the local office. | ☐
60 days out | Fire marshal and occupancy inspection dates scheduled. | ☐
60 days out | Equipment delivery dates confirmed with every vendor; install and start-up scheduled around the build-out. | ☐
60 days out | Kitchen equipment list checked against the final menu; nothing missing, nothing extra. | ☐
60 days out | Menu locked for opening; no further recipe changes after this date. | ☐
60 days out | Recipe cards costed for every locked item, food cost percent checked against target before the menu is printed. | ☐
60 days out | Training plan built: a shift-by-shift schedule for opening week naming who trains which station. | ☐
60 days out | Trainers named from existing stores; travel and lodging booked. | ☐
60 days out | Soft-open and marketing dates set; local outreach to neighbors, social and press started. | ☐
60 days out | Bank account and card-processing merchant account opened for the new location. | ☐
60 days out | Uniforms ordered and sized for the confirmed headcount. | ☐
30 days out | Front and back of house crew hired to full headcount. | ☐
30 days out | Food handler cards and any required alcohol-service certification on file for every new hire. | ☐
30 days out | Onboarding paperwork ready for day one: offer letters, tax forms, direct deposit. | ☐
30 days out | SOPs, opening and closing checklists and prep lists loaded into the new store, in the same format as the rest of the group. | ☐
30 days out | Par levels set by vendor and item; first delivery dates confirmed. | ☐
30 days out | POS menu, modifiers and pricing tested end to end on the actual terminals. | ☐
30 days out | Cash handling and till procedures set and posted for the new store. | ☐
30 days out | Mock service run with staff only: full menu, timed, no guests. | ☐
30 days out | Second mock service run with invited guests: full sequence, kitchen and pass timed. | ☐
30 days out | Health inspection passed and permit posted where required by law. | ☐
30 days out | Liquor license, business license and local permits received and posted. | ☐
30 days out | Insurance certificates on file for the new location. | ☐
30 days out | Emergency contact list, evacuation plan and first-aid kit in place. | ☐
Opening week | Friends and family night run at reduced capacity before any paying guest. | ☐
Opening week | Soft open started with a limited menu and reduced hours. | ☐
Opening week | Temperature logs and opening and closing checklists live from the first shift, not phased in later. | ☐
Opening week | Cash procedures run exactly as trained: till counts, drops, two-person verification. | ☐
Opening week | Daily manager debrief held after every shift: what broke, what gets fixed before tomorrow's shift. | ☐
Opening week | Ticket times and guest wait times tracked and reviewed at the daily debrief. | ☐
Opening week | 86 list and any menu adjustment communicated to every shift before service. | ☐
Opening week | District manager or owner on site for the full opening week. | ☐
Opening week | Nightly walkthrough of the kitchen and dining room for safety and cleanliness. | ☐
Opening week | Full menu and regular hours launched once soft-open numbers hold steady for three straight days. | ☐
First 30 days | Labor cost and prime cost calculated weekly and checked against the group's target. | ☐
First 30 days | First full inventory count and variance check run at day 30. | ☐
First 30 days | Guest reviews across Google, delivery apps and social monitored and answered daily. | ☐
First 30 days | 30-day check-in held with every new hire. | ☐
First 30 days | GM's 30-day review held with the district manager or owner. | ☐
First 30 days | Opening punch list (contractor callbacks, equipment fixes) closed out. | ☐
First 30 days | Opening budget reconciled against actual spend, with the variance written down. | ☐
First 30 days | Trainers sent back to their home stores; the local team runs every shift on its own. | ☐
First 30 days | Store moved from the opening staffing schedule to the group's standard steady-state schedule. | ☐
First 30 days | Handoff meeting held: the opening checklist is retired and the store moves onto the standard weekly ops cadence. | ☐
First 30 days | First formal district manager visit or store audit scheduled. | ☐
Version this sheet every time you open a unit (v1, v2, v3) and note what changed. The opening lead keeps it day to day; the district manager or owner signs off before the store moves to steady-state.